## Sponsor Inputs (hidden)
# | High level ideas / Features
1 | Create Account
2 | View Restaurants
3 | Search Restaurants
4 | View Menu
5 | Add to Cart
6 | Purchase
7 | Restaurant views order
8 | Restaurant marks order as delivered
Notes:
1 | The above points were listed as draft ideas by the project sponsor.
2 | The project sponsor mentioned that he wants to compete against Talabat.
3 | As a sponsor, I am planning to compete against Talabat.
4 | This is a view only file, you can make a copy then edit in the copy.
5 | You can find a tab named Product Backlog Template, please feel free to use it when creating your product backlog.

## Product Backlog Template
# | Epic | User Story | Priority | Ready to be planned | Planned Sprint | Status
1 | Create Account | As a user, I want to create account, to save my contact Address. | High | Week 1 of November | 1 | Awaiting Intial Meeting
|  | As a user, I want to create account, to bookmark favorite restaurant. | High | Week 1 of November | 1 | Awaiting Intial Meeting
|  | As a user, I want to create account, to add personal reviews. | High | Week 1 of November | 1 | Awaiting Intial Meeting
|  | As a restraurant, I want to have visibility of number of users using my application. | High | Week 1 of November |  | Awaiting Intial Meeting
2 | Reset Account Password | As a User, I want to reset password, to be able to stay safe/reset forgot password. | High | Week 1 of November | 1 | Awaiting Intial Meeting
|  | As app owner, I want user to reset password every 90 days, to make sure their details are secured. | High | Week 1 of November | 1 | Awaiting Intial Meeting
3 | View Restaurants | As a user, I want to view restaurants in my area, to be able to choose the closest restauant | High | Week 1 of November | 1 | Awaiting Intial Meeting
4 | Search Restaurants | As a user, I want to search for my preferred restaurant. | High | Week 1 of November | 1 | Awaiting Intial Meeting
|  | As a user, I want to be able to filter by cuisine. | Low | Week 1 of December | 2 | Awaiting Intial Meeting
|  | As a restaurant, I want to be able to segment restarants by cuisines. | Low | Week 1 of December | 2 | Awaiting Intial Meeting
5 | View Menu | As a user, I want to be able to view the menu, to be able to see the prices. | High | Week 1 of November | 1 | Awaiting Intial Meeting
|  | As a user, I want to be able to see recent offers, to be able to check new menu items. | High | Week 1 of November | 1 | Awaiting Intial Meeting
|  | As a user, I want to have scanned menu, so I can see how the food looks like in picture. | High | Week 1 of November | 1 | Awaiting Intial Meeting
6 | Vote Menu Items | As a user, I want to vote on menu items, to be ale to share which dish/item I loved most | Medium | Week 3 of December | 3 | Awaiting Intial Meeting
|  | As a restaurant, I want to view menu vote, to be able to collect analytics about which item has the most interest to be considered in any new item added to the menu | High | Week 1 of November | 1 | Awaiting Intial Meeting
7 | Add to Cart | As a User, I want to be able to add to cart, to collect all my orders under one basket. | High | Week 1 of November | 1 | Awaiting Intial Meeting
|  | As a restaurant, I want to be able to see users cart, to be able to organize orders. | High | Week 1 of November | 1 | Awaiting Intial Meeting
8 | Purchase | As a user, I want to have multiple payment options, to pay by COD/Visa, or any other preferred methods | High | Week 1 of November | 1 | Awaiting Intial Meeting
|  | As a restaurant, I want to be able to provide payment options, to be able to provide different payment methods. | High | Week 1 of November | 1 | Awaiting Intial Meeting
9 | Reviews | As a user, I want to be able to submit review, to share my experience with other shoppers and restaurant. | High | Week 1 of November | 1 | Awaiting Intial Meeting
|  | As a restaurant, I want to see reviews, to check feedback and help to improve customer experinece. | High | Week 1 of November | 1 | Awaiting Intial Meeting
|  | As a restaurant, I want to see user reviews, to collect analytics about user preferences. | High | Week 3 of November | 3 | Awaiting Intial Meeting
10 | Restaurant views order | As a restaurant, I want to view orders, to be able to check order time, view requeted items, choose closest restaurant, track delivery ETA | High | Week 1 of November | 1 | Awaiting Intial Meeting
11 | Restaurant marks order as delivered | As a user, I want to see delivery status, to know where my order has been reached. | High | Week 1 of November | 1 | Awaiting Intial Meeting
|  | As a restaurant, to be able to track outgoing orders time ETA and location. | High | Week 1 of November | 1 | Awaiting Intial Meeting